## BurnDownSrint2
Tasks | Completion Time in Days on the 17/10/22 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | Days Work Per Week | Number of Weeks | Based on tutorial found here:
Clean up Enemy Spawner | 0.2 | 0.2 |  |  |  | 2.5 | 4 | https://www.extendoffice.com/documents/excel/2446-excel-burndown-chart-or-burn-up-chart.html
Clean up Wave Handler | 0.2 | 0.1
Expose Variables for Level Designers | 0.1 | 0.1
Create Hardpoint Class | 0.3 | 0.2
Create Hardpoint Manager | 1 | 0.5
Minor Changes to Hardpoint System | 0.2 |  | 0.3
Create EnemyBase class + add seeking | 0.5 |  | 0.5
Refactor Enemy Blueprints to C++ | 1 |  | 1.5
Create Pause Menu | 0.5 |  | 0.5
Redo Spawning for new Enemy Class | 0.2 |  |  | 0.2
Clean up Blueprints due to Enemy Class | 0.5 |  |  | 0.5
Add Score System | 0.5 | / | / | / | /
Add Height Clamp to Spawnpoints | 0.1 |  |  | 0.1
Add Height Clamp to Hardpoints | 0.1 |  |  | 0.1
Redo Character Inputs in C++ | 1 |  |  | 1
//Start of Internet Issues//
Create Area Manager Class | 0.5 |  |  |  | 0.5
Re-Add Pause Menu (GitHub issue) | 0.1 |  |  |  | 0.1
Create Main Menu | 0.5 |  |  |  | 0.3
Fix Blueprints (GitHub issue) | 0.2 |  |  |  | 0.5
GitHub Tech Support | ? |  |  |  | 1.5
Find Fix for NavMesh Bug | 1 |  |  |  | 1
Remaining work days | 10 | 7.5 | 5 | 2.5 | 0
Remaining days worth of work | 6.4 | 1.1 | 2.8 | 1.9 | 0