## BurnDownSrint3
Tasks | Completion Time in Days on the 14/11/22 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | Days Work Per Week | Number of Weeks | Based on tutorial found here:
Reorganise EnemySpawner class | 1 | 0.5 |  |  |  | 2.5 | 4 | https://www.extendoffice.com/documents/excel/2446-excel-burndown-chart-or-burn-up-chart.html
Reorganise WaveHandler class | 1 | 0.5
Add Random Events to Hardpoint | 0.2 | 0.2
Add Despawning/Respawning to Enemies | 0.2 | 0.3
Make Enemies Respawn If Too Far Away | 0.1 | 0.1
GitHub Tech Support | ? | 1 | 0.2 | 0.1
Create ScoreManager | 0.5 |  | 0.2
Add Score Values to Enemies | 0.1 |  | 0.1
Add Score Values to Completing Hardpoint | 0.1 |  | 0.1
Add Score Values to Wave Completion | 0.1 |  | 0.1
Comment Code | 1
Re-do Mouse Input | 0.2 |  |  | 0.3
Add Final Score to Death Screen | 0.1 |  |  | 0.1
Add MainMenu and Restart Button to Death Scene | 0.1 |  |  | 0.1
Create Collisions on Bannisters and Stairs | 0.5 |  |  | 0.4
Redo Enemy Mesh Handling | 0.5 |  |  | 0.5
Redo Base Enemy Blueprints | 0.1 |  |  | 0.1
Redo Miniboss Blueprint | 0.1 |  |  | 0.4
Remaining work days | 10 | 7.5 | 5 | 2.5 | 0
Remaining days worth of work | 3.2 | 2.6 | 0.6 | 0.1 | 0